## Project profile
PW - 002
Project Profile
1 | Name of the Project:
2 | Sector
3 | Location
4 | Sponsoring Ministry/Agency
5 | Executing Agency
6 | Name of Project Director
7 | Postal Address
8 | Telephone |  |  | Office
Res.
9 | Fax No.
10 | E-mail address
11 | Date of approval by |  |  |  | DDWP |  |  | CDWP |  |  |  | ECNEC
12 | Decision of the DDWP
13 | Decision of the CDWP
14 | Decision of the ECNEC
15 | Objectives of the Project
16 | Commencement Date |  |  |  | As per PC-I | [6 empty] | Actual
17 | Completion Date |  |  |  | As per PC-I | [6 empty] | Expected
(Million Rs.)
18 | Approved cost of the Project |  |  |  | Total |  |  |  |  | Local |  |  |  | FEC
(Million Rs.)
19 | Sources of financing |  |  |  | Source of Financing | [6 empty] | Amount
20 | Financial Phasing, Releases & Expenditure
(Million Rs.)
| Year |  | Phasing as per approved PC-I (Latest) |  |  | PSDP Provision |  |  |  |  | Actual Amount Released |  |  |  | Actual Expenditure
|  |  | Total | FEC |  | Total |  |  | FEC |  | Total |  | FEC |  | Total |  | FEC
Total
21 | Itemised cost as per approved PC-1 and Expenditure
(Million Rs.)
| S.No. | Major Items |  |  |  |  | PC-1 Cost Estimates | [5 empty] | Cumulative expenditure upto the end of last financial year
22 | Physical scope of project as per approved PC-I and achievements (In quantifiable terms)
| S.No. | Major Items |  |  |  |  | Unit |  |  | Physical Quantity |  |  |  | Cumulative achievements upto the end of last financial year

## Monitoring Report
PW - 003
MONITORING REPORT FOR ________________
1 | Name Of the Project
2 | Name of Ministry/Division/Agency
(Million Rs.)
3 | Approved/capital cost |  |  |  | Total |  |  | Local |  |  |  | FEC
(Million Rs.
4 | Releases upto the end of last financial year |  |  |  | Total |  |  | Local |  |  |  | FEC
(Million Rs.)
5 | Expenditure upto the end of last financial year |  |  |  | Total |  |  | Local |  |  |  | FEC
(Million Rs.)
6 | PSDP Allocations for the current year |  |  |  | Total |  |  | Local |  |  |  | FEC
(Million Rs.)
7 | Requirements, Releases and Expenditure |  |  |  | Cash require- ment | Amount released |  | Date of release |  | Date the amount reached the project authorities |  |  | Actual Expendi- ture
i. 1st Quarter
ii. 2nd Quarter
iii. 3rd Quarter
iv. 4th Quarter
[5 empty] | Total | 0 | [6 empty] | 0
8 | Reasons if funds are not released
9 | Reasons if funds could not be fully utilized
10 | Financial allocation as per Cash Plan, Releases and expenditure | [9 empty] | ( Million Rs.)
| S.No | Items |  |  | 1st Quarter
[5 empty] | Allocations as per Cash Plan |  | Releases |  |  |  | Expenditure
Total
| S.No | Items |  |  | 2nd Quarter
[5 empty] | Allocation as per Cash Plan |  | Releases |  |  |  | Expenditure
Total
| S.No | Items |  |  | 3rd Quarter
[5 empty] | Allocation as per Cash Plan |  | Releases |  |  |  | Expenditure
Total
| S.No | Items |  |  | 4th Quarter
[5 empty] | Allocation as per Cash Plan |  | Releases |  |  |  | Expenditure
Total
11 | Physical Targets and Achievements (In quantifiable terms)
| S.No | Items |  |  | Unit | 1st Quarter
[6 empty] | Targets |  |  |  | Achievements
| S.No | Items |  |  | Unit | 2nd Quarter
[6 empty] | Targets |  |  |  | Achievements
| S.No | Items |  |  | Unit | 3rd Quarter
[6 empty] | Targets |  |  |  | Achievements
| S.No | Items |  |  | Unit | 4th Quarter
[6 empty] | Targets |  |  |  | Achievements
12 | Appointment of Project Director (Pl. tick the relevant box)
[5 empty] | Full Time |  |  |  | Additional Charge
Position held since(Pl. give date)
13 | Whether Financial/Administrative powers have been delegated to the Project Director (Pl. tick the relevant box) |  |  |  | Yes |  |  |  | No. (Pl. give details)
14 | Overall Implementation of the Project |  |  |  | Intial Stage | On Schedule |  |  | Delayed (Quantify delay in months)
15 | Observations in the last Monitoring Report and action taken |  |  |  | Observations |  |  |  | Action taken
i.
ii.
iii.
iv.
16 | Problems/Bottlenecks in the Project Implementation
|  | Recruitment of Staff |  |  |  | Delay in Release of Funds
|  | Delay in Consultants Appointments |  |  |  | Law & Order Situation
|  | Lack of coordination between Fed/Prov Govts. |  |  |  | Management Capablity
|  | Land Acquisition |  |  |  | Delay in Procurement
|  | Turn over of PD/Staff |  |  |  | Delay in Civil Works
|  | Delay in designing / Consultancy |  |  |  | Other
17 | Indicate only one main problem from the list given below:
|  | Recruitment of Staff |  |  |  | Delay in Release of Funds
|  | Delay in Consultants Appointments |  |  |  | Law & Order Situation
|  | Lack of coordination between Fed/Prov Govts. |  |  |  | Management Capablity
|  | Land Acquisition |  |  |  | Delay in Procurement
|  | Turn over of PD/Staff |  |  |  | Delay in Civil Works
|  | Delay in designing / Consultancy |  |  |  | Other
18 | Observations of the Monitoring Officer |  |  | i.
ii.
iii.
iv.
19 | Recommendations |  |  | i.
ii.
iii.
iv.
Name of Monitoring Officer
Designation/Section
Telephone No.
Date of Monitoring
Date of Reporting

## PC-III (B)
PC-III (B) Form
(Revised - 2005)
Government of Pakistan
Planning Commission
Implementation of Development Projects
(To be furnished by 5th day of each month)
1 | Report for the month of
2 | Name of the Project:
3 | Financial Status
| i) | PSDP allocations for the current year
| ii) | Current quarter requirements as per cash plan
| iii) | Releases during the month
| iv) | Expenditure during the month
4 | Itemized Expenditure during the month under report
| S.No. | Items | Total |  |  |  | Local | FEC
5 | Physical Status
Physical achievements during the month under report
| S.No | Items | Unit |  | Quantities
6 | Output Indicators
7 | Problems/Bottlemecks in Project Implementation
|  | Recruitment of Staff |  | Delay in Release of Funds
|  | Delay in Consultants Appointments |  | Law & Order Situation
|  | Lack of coordination between Fed./Prov. Govts. |  | Management Capablity
|  | Land Acquisition |  | Delay in Procurement
|  | Turn over of PD/Staff |  | Delay in Civil Works
|  | Delay in designing / Consultancy |  | Other